PlanLibre – a basic tutorial – make a Tatin’s pie project
# What You Will Learn
- defining project settings
- defining ressources for a project
- defining tasks of a project
- add images to ressources and tasks
- modify project boundaries, ressources, tasks
- move tasks and understand timeine

Here, we want to teach you with a basic project, basic, but using various features. Suppose that you want to cook a delicious Tatin’s pie (a pie with apples and so on), and the various tasks involve YOU, your son and your daughter.

Figure 1: Tatin's pie, credits : Wikipedia France

Then we have 3 « human forces » among our resources ; but in order to make this pie, we must get cooking tools, ingredients, and so on. Here is the list of resources :

Resources		Cost
Human work force	Me, Son, Daughter	0
Raw materials	Apples (2 kilos or 4 pounds),	6
	Sugar : 0.250 kilo or 1/2 pound	2
	Ready made puff pastry	1
	Butter : 0.125 kilo or 1/4 pound	2
Tools	Soup spoon	0
	Rolling pin	0
	pastry mold	0
	Oven	0.5

When a manager sets up a project, he or she must break down the project in various tasks, like us !

Task	Duration	When ?	Who ?
Go to the library in order to get a recipe book	2 hours	3 days before	Me, son, daughter
Choose a recipe	2 hours	2 days before	Son, daughter
Go to the grocery to buy apples	2 hours	1 day before	Son
Collect tools (apart owen!)	1 hour	Target day	daughter
Prepare ingredients	1 hour	Target day	Me, son, daughter
Mix ingredients	1 hour	Target day	Son
Cook pie	1 hour	Target day	Me
Cool pie	1 hour	Target day	Me
Eat pie	1 hour	Target day	Me, son, daughter
Comment result	3 days (yes, 3!)	Target day	Me, son, daughter

In order to have more fun with PlanLibre, go to Internet, and try to get some free pictures for :
- Tatin Pie
- apples
- cooking book
- cooking tools
- owen
 Please, use only small pictures, it’s better for your computer.

store them on your computer, we will reuse them.

Let’s go !
For all steps, we suppose that you have launched PlanLibre with an empty project.

# 1. Define global properties.
For all steps, we suppose that you have launched PlanLibre with an empty project.

Choose menu Project>properties
A dialog appears.
Fill fields like this screenshot :

You are free to change dates : by default, PlanLibre uses current date.

Once done, click on [Ok] button ; if you are on « home screen », you can see that the display has changed, with the project’s name :

That’s all for properties !

Now, it’s time to add tasks, it’s the second step for you.

# 2. Add tasks to project
We can add tasks in every order, but since it’s a basic tutorial, please follow steps of the previous table. For convenience, I copy this table here :

Task	Duration	When ?	Who ?
Go to the library in order to get a recipe book	2 hours	3 days before	Me, son, daughter
Choose a recipe	2 hours	2 days before	Son, daughter
Go to the grocery to buy apples	2 hours	1 day before	Son
Collect tools (apart owen!)	1 hour	Target day	daughter
Prepare ingredients	1 hour	Target day	Me, son, daughter
Mix ingredients	1 hour	Target day	Son
Cook pie	1 hour	Target day	Me
Cool pie	1 hour	Target day	Me
Eat pie	1 hour	Target day	Me, son, daughter
Comment result	3 days (yes, 3!)	Target day	Me, son, daughter

We proceed step-by-step, and will add only tasks themselves ;, for now.
For example, suppose we want to add the 1st task, « go to the library ... ».
- switch display to task view by clicking the « task » icon on the left side.
- click on the [+] button on upper bar

- a dialog appears, please fill it like me :

I’ve choosen a « blue » color ; fill free to choose yours, and, as usual, don’t matter the date.
Click the [Ok] button, and notice the change on « task display » :

You’ve just started your task list, congratulations !
Since you’ve understood, please proceed on the same way for all other tasks. You should obtain something like that :

Don’t forget to save your project !
And notice the nice « lamp » icon for « choose a recipe » and « comment recipe » : they are intellectual tasks, against other « material » tasks (tool like icon).

# 3. Now, it’s time to add ressources !
In real world, tasks use many resources ; for example, suppose our task is to build a wall, we have to use human workforce, concrete, various tools …
Same thing for our pie ! Her, we reuse the « resources » table.
Launch PlanLibre, reload previous file, and, now, switch to ressource view.

like for tasks, please click on [+] button to add a resource. You can add a resource in any order. A new dialog box appears : as a trial, fill fileds with datas for ressource «apples» :

Ressources		Cost
Human work force	Me, Son, Daughter	0
Raw materials	Apples (2 kilos or 4 pounds),	6
	Sugar : 0.250 kilo or 1/2 pound	2
	Ready made puff pastry	1
	Butter : 0.125 kilo or 1/4 pound	2
Tools	Soup spoon	0
	Rolling pin	0
	pastry mold	0
	Oven	0.5

As an exercice, try,, like me, to change color, and to add a picture.

Once done, click on [Ok] button. The new resource is on top on resources’ list :

As you can see, it’s possible to set an icon for each resource : the source picture is automatically resized (the original file remains unchanged)
Do the same for all resources, you should obtain something like that :

We don’t looking for truth or accuracy, it’s only a training ! Fill free to add pictures, change colors, and so on.
Save your job, the next step is more complex …

# 4. like in true life : associate tasks and ressources
No task without resources ! So, we will learn to associate (assign) one or more ressource to various tasks.
In order to achieve that, please switch to task view, and get in mind this table :

Task	Duration	When ?	Who ?	With ?
Go to the library in order to get a recipe book	2 hours	3 days before	Me, son, daughter
Choose a recipe	2 hours	2 days before	Son, daughter
Go to the grocery to buy apples	2 hours	1 day before	Son
Collect tools (apart owen!)	1 hour	Target day	daughter
Prepare ingredients	1 hour	Target day	Me, son, daughter	Apples, sugar, ready made pastry, butter, tools
Mix ingredients	1 hour	Target day	Son	Apples, sugar, ready made pastry, butter, tools
Cook pie	1 hour	Target day	Me	owen
Cool pie	1 hour	Target day	Me
Eat pie	1 hour	Target day	Me, son, daughter
Comment result	3 days (yes, 3!)	Target day	Me, son, daughter

How to do that ?
 In task view, for each task, click on button :

then we reopen the task dialog. For example, let’s open the « Go to the library » task ; you should see something new :

Please have a look on lower left side : we can see the list of available resources : click on Me, Son and Daughter resources, then click [ok] button.
Notice the change on task View :

Now, for the « Go to the library » task, used resources are displayed.
Since you attempt to reuse ressources Son & Daughter on this task, at the same period than they are already used on task « Go to the library … « , PlanLibre displays a warning dialog, like this :

It isn’t an error, only a warning, take it easy !

Do the same for all tasks, according to previous table. Don’t forget to save your job. You should obtain something like that (I used various pictures for my resources) :

# 5. Hey doc, there’is something wrong on the timeline !
Please, switch to timeline view. You should see something like that :

Gasp ! All tasks seems to be aligned on the same day ! We have to work better. As you can remind, «the « Go to the library » task is defined 3 days before other tasks. Then, we have to change project starting date, and, after, move this task along the timeline.
Let’s go !
- first, go to menu project>poperties. Then, change the starting date in order your project starts 3-4 days before. This step will change project’s boundaries, and it’s a very useful skill for many projects !
Click on starting date button, a calendar dialog appears :

choose a new date, click [Ok] → the calendars disappears ; then click [ok] button for properties dialog.

- Now, we will change the starting date of the « Go to the Library … «  task. I will teach you the two ways ; first way, by modifying task, second way by moving directly on timeline. Choose as you want !
- if you want to use the dialog way (#1), switch to task view, and click on modification button for the task « Go to the library ... ». On the dialog, change the starting date, and click [Ok] button.

- if you want to use only the mouse, switch to « timeline view ». Move mouse pointer to the task « Go to library ». Left click, and withour releasing left button, move the pointer to the left : you can see a colored rectangle, as a shadow of the task. Once you’ve reached the true starting day, release left button. It’s done !

And, of course, if you switch to « task view » and click on « modify » button of this task, you can check that the starting date is automatically updated.